## Cover
For internal use only
Omega Aerosystems |  |  | Project Falcon
Document ID
Risk Management Plan

Status | in work |  |  |  |  | Versioncheck
Version | 1.0_001 |  |  |  |  | 1.0_001
Date | 2017-07-03 |  |  |  |  | 2
4
1
Responsible | José Reginaldo Hughes Carvalho |  |  |  |  | 0
001
Author(s) | José Reginaldo Hughes Carvalho |  |  |  |  | TRUE
TRUE
TRUE
Release | [5 empty] | TRUE
Status:released |  | Version: 1.0_002 |  | Date: 29/06/2004
The information contained herein is confidential and the property of Omega Aerosystems and is supplied without liability for errors or omissions. No part may be reproduced or used except as authorised by contract or other written permission. The copyright and the foregoing restriction on reproduction and use extend to all media in which the information may be embodied. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Published by | Omega Aerosystems
Note on F6: GENERAL USAGE GUIDELINES Specify the document attributes (organizational unit, document scope, identifier, title, status, version, etc.) only on the cover sheet. The footer lines on all sheets use references to the text entered here and are actualized automatically by macro when the document is being saved. The format and layout of the cover sheet including header and footer lines must not be changed. If the document is uniquely identified by the "Scope" (e.g. the project or component name) and the "Title" (e.g. the name of an artefact required by the development process), the separate attribute "Identifier" may be omitted. The attributes "Status" and "Version" are mandatory for documents that are regularly changed or formally approved. The "Release" signature is only required for documents that are officially released.

## History of Change
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2017-07-01 | Reginaldo | In Work | First draft
Note on A4: Louis Peter: Format “x.y_zzz”. The version string consists of the planned major “x” and minor “y” version, and the editorial revision or step “zzz” which starts from 001 with each new planned version "x.y". Thus the first version string is “1.0_001”.

## Guideline
Guideline
The purpose of this template is to provide maximum control over project risks with a minimum of effort using one single risk management plan in the risk management process.
The work with this template comprises the following steps:
Instantiation of template
Adjust parameters in worksheet Risk Classes
Risk identification
Document identified risks in worksheet Risk Plan, area Risk Identification.
Risk assessment
Document risk probability and impact in worksheet Risk Plan, area Risk assessment
Risk handling
Document risk handling activities in worksheet Risk Plan, area Risk handling
Risk reporting
The generation of the reports (worksheet Risk Report) is automated by the template.
Chapter 4 : Risk reporting
► Risk controling and reporting is part of the project leaders responsibility and is part of project controling and reporting, respectively.
► The objective of risk controling and reporting is
(1) to periodically review the risks in the context of the project’s current status and circumstances,
(2) to revise the documentation of the risks, as additional information becomes available, and
(3) to communicate the risk status to those affected.
► This risk management plan shall be updated regularly, preferably weekly, at least prior to every milestone declaration. For detailed regulations refer to the applicable development process, reporting procedures or project specific regulations.
► Along with the risk list itself, the risk report is used to communicate the current status of the risk exposure of the project to senior management and other stakeholders.
► The generation of the data and the diagrams in the worksheet "Risk Report" is automated in this template; the layout must not be changed.
► The total risk impact shows the total cost increase and schedule delay, weighted by probability, of all identified risks. In practice, schedule delays of several risks usually will not simply add up, but nevertheless the number gives an estimate of the possible schedule delay in the project.
► The background color of the total risk exposure changes from green to yellow, and then to red, to reflect the overall risk status of the project, as the risk exposure number reaches the values 0.3 and 1.0, respectively.*
► The axis and the scaling of the risk portfolio of the top10 risks is automatically adjusted and reflects the selection of the assessment mode.
* These numbers correspond to the thresholds of the two risk classes "Critical" and "Disastrous", respectively.

## Risk Classes
TRUE
TRUE
Project data |  | Planned schedule |  | Planned cost |  |  | TRUE
FALSE
|  | 930 | days | 1700000 | Reais
Risk classes |  | Schedule delay |  | Cost increase
Disastrous | ≥ | 20 | days | 300000 | Reais | Missing links
Critical | ≥ | 6 | days | 90000 | Reais
Undesired | ≥ | 2 | days | 30000 | Reais
Tolerable | ≥ | 0 | days | 0 | Reais
Please specify the thresholds for the highest risk class with respect to schedule delay and cost increase for your project, as appropriate. The thresholds for the other risk classes are calculated accordingly. The planned project data is optional and may be documented simply for comparison. The thresholds of the highest risk class are used to caculate the normalized risk exposure: [Risk Exposure] = [Risk Probability] x [Risk Impact], where [Risk Impact] = [Schedule Impact] + [Cost Impact]. * The values in brackets are dimensionless numbers, and the units are defined by the thresholds of the highest risk class. * Note that each risk can have an impact either on the schedule, or the cost, or on both.

## Config (hidden)
Disastrous | 1 | 2 | 0.875 | 20 | 300000 | 40 | 600000
Critical | 0.3 | 0.65 | 0.625 | 6 | 90000 | 13 | 195000
Undesired | 0.1 | 0.2 | 0.375 | 2 | 30000 | 4 | 60000
Tolerable | 0 | 0.05 | 0.125 | 0 | 0 | 1 | 15000
Red | 1
Yellow | 0.3
Green | 0

## Risk Plan
[12 empty] | Shown | Shown | [7 empty] | Config!A1 | Disastrous | Active | 10%
|  | Risk identification |  |  | Risk identification | Risk assessment | [6 empty] | Risk assessment | Risk handling |  |  |  |  | Risk handling |  | Config!A2 | Critical | Occurred | 40%
[12 empty] | 2025-09-30 | [8 empty] | Config!A3 | Undesired | Cancelled | 60%
[10 empty] | Total | Total | 0.155 | [8 empty] | Config!A4 | Tolerable | Problem | 90% |  |  |  | TRUE | TRUE | TRUE | FALSE
No. | Risk description | Implication on project | Raised by | Status | Identification date | Last change date | Probability | Schedule impact [class] | #N/A | Cost impact [class] | #N/A | Exposure | Risk class | Risk handling activity | Trigger | Responsible | Planned date | Planned cost | Status | One | Weighted s.imp. | Weigthed c.imp. | Normalized s.imp. | Normalized c.imp. | Derived s.imp. | Derived c.imp. | Risk [Y/N] | Active s.imp. link | Active c.imp. link | Missing s.imp. link | Missing c.imp. link
1 | Falta de engajamento da equipe | Pode gerar atrasos, retrabalho e baixa qualidade do software. | Equipe do projeto | Active | 2025-09-25 | 2025-09-29 | 40% | Tolerable | 1 | Tolerable | 15000 | 0.04 | Tolerable | Acompanhamento semanal, reuniões Scrum, divisão equilibrada de tarefas. | Ausência de membros em mais de 2 reuniões seguidas. | Scrum Master | Durante todo o projeto | 0 | Active | 1 | 0.4 | 6000 | 0.125 | 0.125 | 1 | 15000 | 1 | TRUE | TRUE | FALSE | FALSE
2 | Atrasos nas entregas parciais | Compromete o cronograma final, reduzindo tempo para testes e ajustes. | Equipe | Active | 2025-09-25 | 2025-09-29 | 60% | Disastrous |  | Tolerable | 15000 | 0.03 | Tolerable | Uso de Scrum com sprints curtos, priorização de requisitos “Must”. | Sprint não concluída no prazo planejado. | Product Owner e Scrum Maste | Durante todo o ciclo | 0 | Planned | 1 | 0 | 9000 | 0.875 | 0.125 | 40 | 15000 | 1 | FALSE | TRUE | TRUE | FALSE
3 | Limitações técnicas dos integrantes | Pode gerar retrabalho, falhas na implementação e aumento do tempo de desenvolvimento. | Equipe | Active | 2025-09-25 | 2025-09-29 | 40% | Undesired |  | Tolerable | 15000 | 0.02 | Tolerable | Divisão equilibrada de tarefas, capacitação rápida, apoio do orientador. | Dificuldade técnica reportada em backlog ou revisão de sprint | Equipe de desenvolvimento | Até Sprint 2 | 0 | Active | 1 | 0 | 6000 | 0.375 | 0.125 | 4 | 15000 | 1 | FALSE | TRUE | TRUE | FALSE
4 | Problemas no controle de estoque (RF-11) | Pode levar a inconsistência no inventário, falta de produtos e perda de confiabilidade do sistema. | Analista de Requisitos | Active | 2025-09-25 | 2025-09-29 | 40% | Critical |  | Tolerable | 15000 | 0.02 | Tolerable | Revisão do módulo de estoque, testes automatizados em cenários de limite mínimo. | Falha em teste de alerta de estoque baixo. | Devs backend e frontend | Sprint 4 | 0 | Planned | 1 | 0 | 6000 | 0.625 | 0.125 | 13 | 15000 | 1 | FALSE | TRUE | TRUE | FALSE
5 | Falha na autenticação e controle de acesso (RF-07 e RF-08) | Pode comprometer a segurança e expor dados sensíveis. | Equipe de segurança | Active | 2025-09-25 | 2025-09-29 | 40% | Critical |  | Tolerable | 15000 | 0.02 | Tolerable | Revisão de código, bibliotecas seguras, testes de penetração básicos. | Falha em teste de login ou acesso indevido. | Devs backend | Sprint 3 | 0 | Planned | 1 | 0 | 6000 | 0.625 | 0.125 | 13 | 15000 | 1 | FALSE | TRUE | TRUE | FALSE
8 | Riscos de compatilbilidade | Usuários não conseguem acessar o sistema em certos dispositivos | Equipe | Active | 2025-09-25 | 2025-09-29 | 10% | Undesired |  | Tolerable | 15000 | 0.005 | Tolerable | Testes de usabilidade em vários dispositivos | Falha em testes de implementação | Equipe de desenvolvimento | Durante todo o ciclo | 0 | Planned | 1 | 0 | 1500 | 0.375 | 0.125 | 4 | 15000 | 1 | FALSE | TRUE | TRUE | FALSE
6 | Dependencia Externa | Atrasos na entrega de informações ou aprovações que podem bloquear o projeto | Product Owner | Active | 2025-09-25 | 2025-09-29 | 40% | Undesired |  | Tolerable | 15000 | 0.02 | Tolerable | Comunicação clara e prazos acordados. | Não recebimento de informações/artefatos do fornecedor ou cliente até a data combinada | Product Owner | Durante todo o ciclo | 0 | Planned | 1 | 0 | 6000 | 0.375 | 0.125 | 4 | 15000 | 1 | FALSE | TRUE | TRUE | FALSE
1 | [10 empty] | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
4 | [10 empty] | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
10 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
11 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
12 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
13 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
14 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
15 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
16 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
17 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
18 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
19 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
20 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
21 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
22 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
23 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
24 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
25 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
26 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
27 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
28 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
29 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
30 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
31 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
32 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
33 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
34 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
35 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
36 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
37 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
38 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
39 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
40 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
41 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
42 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
43 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
44 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
45 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
46 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
47 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
48 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
49 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE
50 | [8 empty] | 0 |  | 0 | 0 | [7 empty] | 1 | 0 | 0 |  |  | 0 | 0 | 0 | FALSE | FALSE | FALSE | FALSE

## Risk Report
Risk report
Project : Project Falcon |  |  |  | Date: | 2017-07-03
Risk assessment
Risk class count |  | Total risk impact
Disastrous | 0 | Schedule delay | 0.4 | days
Critical | 0 | Cost increase | 40500 | Reais
Undesired | 0
Tolerable | 7 | Risk exposure | 0.155 |  |  | 1
0.3
0
Risk portfolio - Top10 risks
Schedule delay [working days]
Schedule impact [class]
Cost increase [Euro]
Cost impact [class]
Probability
Note on H4: Risk impact: The total risk impact is calculated as ∑ [Impact] x [Probability] over all risks in the worksheet "Risk Plan". If the risk impact was assessed by classification, the numerical values of [Impact] for each risk are assumed to be the average impact value of the corresponding risk class, respectively twice the threshold for the highest risk class.
Note on F7: Total schedule delay: The total schedule delay is calculated assuming that the schedule delays of all risks that occur (according to the estimated probability) simply add up, which might indeed happen but is certainly not the general case. So this number represents some kind of "worst case szenario" and should be compared with the estimated schedule delays of the individual risks to obtain a realistic picture.
Note on F10: The background color of the total risk exposure changes from green to yellow, and then to red, to reflect the overall risk status of the project, as the risk exposure number reaches the values 0.3 and 1.0, respectively. These numbers correspond to the thresholds of the two risk classes "Critical" and "Disastrous", respectively.
Note on H13: Top10: Note that the list of top10 risks may depend on the sorting criteria. The axis and the scaling of the risk portfolio of the top10 risks is automatically adjusted.
Note on L15: The sorting criterion influences the Top10 selection. Eg sorting by "Schedule impact" selects the 10 risks with the highest schedule impact.
Risks sorted by
Tolerable
Undesired
Critical
Disastrous
Tolerable
Undesired
Critical
Disastrous